## Sheet1
Date & Time | Milestone | Dependencies | Coordinator(s) | How many people needed | Location | Questions/what is needed
| Call for Entries (web) | Need location, location of reception, dates |  |  |  | How long should the registration be open?
| Send postcards | arrange desktop publisher, provide art and text |  |  |  | registration form - does this need a review?
| Registration form edits complete | provide art and text, are any reviews or approvals needed? |  |  |  | posters, postcards, etc.
| Registration Open (form live) |  |  |  |  | reception planning
| Receive, photograph and process artwork | can be shipped, or brought in |  |  |  | labels for pieces | lable format
| Registration End |  |  |  |  | pens, pencils, tape, printer, paper and lables
| Print spreadsheet of entries (2 copies) |  |  |  |  | site map showing where each case will be installed
Preliminary case design completed
Lists of artwork and values for [exhibition site]
| Pickup and deliver cases to exhibition site |  |  |  |  | location to receive and process shipped artwork
| Assemble cases |  |  |  |  | photographer for all art work on day artwork is received
| Unpack and populate cases with artwork |  |  |  |  | display cases | what is needed for this?
| [exhibition site] Installers begin installation process? |  |  |  |  | case designers | what is needed for this?
| Final adjustments to artwork in cases |  |  |  |  | case installers (Exhibition site owners and SMG) | what is needed for this?
| [exhibition site] installers move cases and artwork |  |  |  |  | Photographer of installations for SMG? | do we have names?
| Mount cases |  |  |  |  | Location for artists to pickup work
| Labels |  |  |  |  | Location for reception, needs to be coordinated and anounced
Final cleaning/QA check
Large wall pieces (not in cases)
Photos of people working /process photos
Exhibition opens
Exhibition reception at XXXX
Exhibition closes
Dismount cases
Pack cases
Box artwork
Artists pick up large work at [designated exhibition site]
Work shipped to artists
Last day to pick up work at [designated site]